## Quant_Risk_Register
Risk ID | Description | Asset Value (AV ₹) | Exposure Factor (EF %) | SLE (₹) | Annual Rate of Occurrence (ARO) | ALE (₹) | Control | Control Cost (Annual ₹) | Residual EF % | Residual ARO | Residual SLE (₹) | Residual ALE (₹) | Risk Reduction (₹) | ROSI (%) | Risk Owner | Review Date
Q1 | Phishing - Customer Emails | 1000000 | 40 | 400000 | 0.3 | 120000 | Email Filter + Training | 70000 | 10 | 0.1 | 100000 | 10000 | 110000 | 57.1429 | Security Lead | 2025-12-31
Q2 | Ransomware - File Servers | 1500000 | 60 | 900000 | 0.2 | 180000 | Backups + EDR | 120000 | 20 | 0.05 | 300000 | 15000 | 165000 | 37.5 | IT Ops | 2025-12-31
Q3 | Data Breach - Customer DB | 2000000 | 50 | 1000000 | 0.15 | 150000 | Encryption + IAM | 150000 | 25 | 0.04 | 500000 | 20000 | 130000 | -13.3333 | CISO | 2025-11-30
Q4 | System Outage - ERP | 1200000 | 45 | 540000 | 0.12 | 64800 | DR & Redundancy | 50000 | 15 | 0.05 | 180000 | 9000 | 55800 | 11.6 | Ops Manager | 2026-01-15
Q5 | Insider Data Theft - HR | 800000 | 55 | 440000 | 0.18 | 79200 | DLP + Monitoring | 80000 | 20 | 0.07 | 160000 | 11200 | 68000 | -15 | HR Head | 2026-03-01

## HeatMap_ALE
Risk ID | Description | ALE (₹) | Residual ALE (₹) | Risk Level (by ALE)
Q1 | Phishing - Customer Emails | 120000 | 10000 | High
Q2 | Ransomware - File Servers | 180000 | 15000 | High
Q3 | Data Breach - Customer DB | 150000 | 20000 | High
Q4 | System Outage - ERP | 64800 | 9000 | Medium
Q5 | Insider Data Theft - HR | 79200 | 11200 | Medium

## Risk_Treatment
Risk ID | Risk | ALE (₹) | Treatment Option | Control | Control Cost (₹) | Residual ALE (₹) | Annual Benefit (₹) | ROSI (%) | Owner | Target Date | Status
Q1 | Phishing - Customer Emails | 120000 | Mitigate | Email Filter + Training | 70000 | 10000 | 110000 | 57.1429 | Security Lead | 2025-12-31 | Open
Q2 | Ransomware - File Servers | 180000 | Mitigate | Backups + EDR | 120000 | 15000 | 165000 | 37.5 | IT Ops | 2025-12-31 | Open
Q3 | Data Breach - Customer DB | 150000 | Mitigate | Encryption + IAM | 150000 | 20000 | 130000 | -13.3333 | CISO | 2025-11-30 | Open
Q4 | System Outage - ERP | 64800 | Mitigate | DR & Redundancy | 50000 | 9000 | 55800 | 11.6 | Ops Manager | 2026-01-15 | Open
Q5 | Insider Data Theft - HR | 79200 | Mitigate | DLP + Monitoring | 80000 | 11200 | 68000 | -15 | HR Head | 2026-03-01 | Open