## Risk Register
Risk ID | Risk Description | Asset / Process Affected | Risk Owner | Likelihood (1-5) | Impact (1-5) | Risk Score (Auto) | Risk Level (Auto) | Existing Controls | Control Reference (ISO/NIST) | Residual Risk Level | Status | Review Date | Comments
RSK-001 | Phishing attack may compromise credentials | Email System | IT Security | 4 | 5 | 20 | High | Email gateway, user awareness | ISO A.7.2.2 / NIST PR.AT-1 |  | In Progress | 2026-01-15 | Need to enhance training
RSK-002 | Firewall misconfiguration | Network Infrastructure | Network Team | 3 | 4 | 12 | Medium | Firewall rule review | ISO A.13.1.1 / NIST PR.AC-5 |  | Open | 2025-12-31 | Quarterly review required
RSK-003 | Data leakage from cloud storage | AWS S3 Buckets | Cloud Admin | 5 | 5 | 25 | High | Access control, encryption | ISO A.10.1 / NIST PR.DS-1 |  | Open | 2026-02-10 | Perform S3 audit

## Risk Heat Map
| Impact 1 | Impact 2 | Impact 3 | Impact 4 | Impact 5
Likelihood 1 | 1 | 2 | 3 | 4 | 5
Likelihood 2 | 2 | 4 | 6 | 8 | 10
Likelihood 3 | 3 | 6 | 9 | 12 | 15
Likelihood 4 | 4 | 8 | 12 | 16 | 20
Likelihood 5 | 5 | 10 | 15 | 20 | 25

## Treatment Plan
Risk ID | Risk Description | Risk Owner | Likelihood (1-5) | Impact (1-5) | Risk Score (Auto) | Risk Level | Existing Controls | Proposed Controls / Mitigation Actions | Control Owner | Target Date | Residual Risk Level | Status (Open/In Progress/Closed) | Review Date | Remarks
RSK-001 | Phishing attack may lead to credential compromise | IT Security | 4 | 5 | 20 | High | Email filtering, user awareness training | Implement multi-factor authentication (MFA) for all employees | Security Admin | 2025-12-15 | Medium | In Progress | 2026-01-15 | Ongoing awareness sessions planned
RSK-002 | Unpatched firewall vulnerability | Network Team | 3 | 4 | 12 | Medium | Firewall monitoring | Patch firmware and enable auto-updates | Network Engineer | 2025-11-30 | Low | Open | 2025-12-31 | Patch scheduled this month
RSK-003 | Data backup failure during outage | IT Operations | 2 | 5 | 10 | Medium | Manual backups | Automate daily incremental backups with cloud redundancy | Backup Admin | 2026-01-10 | Low | Open | 2026-02-10 | Automation testing in progress
Residual Risk Level | Count
Medium | 1
Low | 2
Status (Open/In Progress/Closed) | Count
In Progress | 1
Open | 2

## Dashboard
Risk Level | Count
High | 2
Medium | 1
Low | 0